## STEPS+TIMING
BATHROOM RENOVATION STEPS & TIMING
*Link to Pinterest Board or other relevant websites*
TASK | DIY OR HIRE OUT | TIMING | PRODUCTS | LINK TO TUTORIAL | DETAILS & CONSIDERATIONS | COMPLETE
Measure and photograph every part of bathroom prior to demo
Pre-demo dumpster drop-off
Demo bathroom
Plan out molding boxes before roughing electrical wires
Electrical: rough wires for sconces, overhead light, ceiling vent
Install tub
Install shower valve
Install mold-resistant sheetrock on walls |  |  | Mold resistant sheetrock
Tape + mud drywall (2-3 coats w/ 24 hours between each)
Install Hardie board around the shower with shower niche |  |  | Hardie Board
Install hardie board on floor |  |  | Hardie Board
Prime the walls: 2 coats of Killz |  |  | Killz
Waterproof entire shower wall area: two coats |  |  | Aqua Defense + Waterproofing mesh tape
Tile shower walls + wait 48 hours to seal marble |  |  | Marble sealer
Tile floor + wait 48 hours to seal marble
Grout shower tile |  |  | Unsanded grout
Grout floor tile |  |  | Unsanded grout
Seal all tile post-grouting
Caulk around tub and floor with silicone sealant
Install vanity
Schedule fabricator to come template the sink and backsplash |  |  |  |  | Need to choose slabs at this point if using stone
Fabricator to install countertop
Install toilet
Install the shower head, vanity top, sink and vanity faucet
Install new casing + hang door
Paint 2 coats on walls and ceiling
Install crown molding
Install baseboard, case molding and door
Install box & chair rail molding
Caulk and fill holes in molding
Paint 1-2 more coats on walls, ceiling and trim
Install light fixtures (ceiling, sconces)
Install cabinet hardware
Install towel bar and toilet paper holder
Install window treatments (roman shade)
Install shower curtain and rod
Hang art
Accessorize/add finishing touches (soap dish, flowers, trinket tray)
/fin & ENJOY :)

## PURCHASE LIST
PRODUCT SOURCING
| PRODUCT | LINK | QTY | COST | ORDERED | DELIVERED | INSTALLED
Shower tile
Floor tile
Trim tile for finishing shower
Brass schluter edge for niche
Alcove tub
Unsanded grout for shower
Unsanded grout for floor
Sconces
Sconce shades
Flush mount
Ceiling vent/fan
Paint for walls + ceiling
Paint for trim and door
Shower curtain
Shower rod
Shower curtain hooks
Outlets
Switchplates
Transition threshold for door
Waste basket
Marble for vanity countertop
Shower Curtain
Tile leveling system
Crown molding
Wall + chair rail molding
Base molding
Window and door casing
Door
Shower faucet/tub spout (whole trim kit)
Vanity
Toilet
Toilet seat
Sink faucet
Sink
Cabinet pulls
Roman shade
Small runner
Door knob
Vanity knobs
Towel bar
Toilet paper holder
Door stop
Hand towels
Bath towels
Towel ring
Robe hook (behind door)
Vanity tray
Vanity mirror